## Retro
Stakelholder | Mario
scrum master | Mario
product owner | Tim
Team | Thierry, Panu, Flo, Mätu, Fabian, Felix
| What went well | What went poorly | how to improve | responsibility | issue
Retro 1 24.02.2023 | The team collaborated effectively and maintained clear communication. | Some team members were frequently interrupted by ad-hoc requests, affecting their focus on sprint tasks. | Series appointments for stand ups created. | Scrum Master - Mario
Retro 2 07.04.2023 | The newly implemented series appointments improved the focus on sprint tasks. | There were a few dependencies between tasks that weren't identified earlier, leading to delays. | Improve task breakdown and identify dependencies during sprint planning to avoid future delays. | Product owner - Tim
|  | Code review process was delayed due to a lack of time allocated for this task. | Allocate dedicated time for code reviews and assign reviewers in advance. | Scrum Master - Mario
Retro 3 21.04.2023 | The newly implemented automated testing framework improved the quality of the code. | Daily stand-up meetings took longer than necessary; some team members provided overly detailed updates. | Set a time limit for daily stand-up meetings and encourage team members to focus on essential updates. | Scrum Master - Mario
| Code review process improved with dedicated time and pre-assigned reviewers. | The deployment process had some delays due to unresolved environment issues. | Improve the deployment process by addressing environment issues and automating deployment steps. | Team - Mätu | https://github.com/TopInvestor4000/ResourceMaster/pull/25
Retro 4 05.05.2023 | The team managed to complete most tasks on time despite the higher workload.
The team successfully addressed and resolved inputs (multiple projects) raised by stakeholders during the sprint.
Retro 5 19.05.2023
Retro 6 02.06.2023

## schedule
Montag | 20.02. | 27.02. | 06.03. | 13.03. | 20.03. | 27.03. | 03.04. | 10.04. | 17.04. | 24.04. | 01.05. | 08.05. | 15.05. | 22.05.
Freitag | 24.02. | 03.03. | 10.03. | 17.03. | 24.03. | 31.03. | 07.04. | 14.04. | 21.04. | 28.04. | 05.05. | 12.05. | 19.05. | 26.05.
KW | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
SW | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Phase | Setup |  |  |  |  | Development
| determining product vision (including creating product outline, defining requirements, identifying risks), creating product backlogs, estimating expenses and planning, setting up |  |  |  |  | - Sprint planning: negotiating sprint backlog entries
| management and development tools |  |  |  |  | - Sprint implementation: applying agile practices, principles and tools, project management, analysis and design, tests, implementation, integration, deployment, etc.
- Sprint review and retrospective: demonstrating products, reflecting on process, reacting to changes
- Backlog refinement: adapting backlog (setting priorities, assigning roles, refining processes), adjusting time estimates and planning)
Sprint |  |  | 1 |  |  | 2 |  | 3 |  | 4 |  | 5 |  | 6
Planning |  | Sprint 1: Planning |  |  | Sprint 2: Planning |  | Sprint 3: Planning |  | Sprint 4: Planning |  | Sprint 5: Planning |  | Sprint 6: Planning
Retro |  |  |  |  | Sprint 1: |  | Sprint 2: Demo, Retro |  | Sprint 3: Demo, Retro |  | Sprint 4: Demo, Retro |  | Sprint 5: Demo, Retro
Demo, Retro

## Review
Review 1 24.02.2023 | created the basic skeleton and plumbing for the project so that future sprints can be truly add incremental value in an efficient way.
Minimal design up front is done so that emergent design is possible in future sprints.
Setup GitHub, Project Vision (half page), Task board
Add project to Table of projects (https://github.zhaw.ch/meea/Software_Projekt_4)
Team presented what it accomplished
Review 2 07.04.2023 | The daily meetings helped us to work on the tasks. even if the appointment does not always work for all participants.
Team presented what it accomplished
Demo of new features
Demo of deployment (and environments)
Review 3 21.04.2023 | As stated in the planning 3, the resources for this sprint were very reduced.
c4Model
Team presented what it accomplished
Review 4 05.05.2023 | Team presented what it accomplished
Review 5 19.05.2023
Review 6 02.06.2023

## Job Description
Scrum Master
Facilitating Scrum Events: One of the primary responsibilities of a Scrum Master is to facilitate Scrum events such as Sprint Planning, Daily Scrum, Sprint Review, and Sprint Retrospective. The Scrum Master ensures that these events are conducted effectively, efficiently, and within the timebox.
Coaching and Mentoring: A Scrum Master acts as a coach and mentor to the Scrum Team, helping team members to understand and implement Scrum principles and practices, as well as guiding them towards continuous improvement.
Removing Impediments: The Scrum Master is responsible for identifying and removing impediments that are preventing the Scrum Team from achieving their Sprint Goal. This involves working with the Product Owner and Development Team to find solutions to the impediments.
Facilitating Communication: A Scrum Master helps facilitate communication and collaboration within the Scrum Team and with external stakeholders. This involves ensuring that information is shared transparently and that everyone is aware of the progress being made.
Protecting the Scrum Team: A Scrum Master protects the Scrum Team from external disruptions and distractions, allowing the team to focus on their work and achieve their Sprint Goal.
Product Owner
Defining and Prioritizing Product Backlog: One of the primary responsibilities of a Product Owner is to define and prioritize the Product Backlog, which contains the list of features, enhancements, and bug fixes that need to be implemented in the product. The Product Owner works with stakeholders to identify and prioritize the most important items.
Communicating Product Vision: The Product Owner communicates the product vision to the Scrum Team and other stakeholders, ensuring that everyone understands the direction of the product and the goals that need to be achieved.
Collaborating with the Scrum Team: The Product Owner collaborates with the Scrum Team to ensure that the items in the Product Backlog are well understood, estimated, and ready for implementation. The Product Owner also works with the Scrum Team to refine and reprioritize the backlog as needed.
Accepting Completed Work: The Product Owner is responsible for accepting completed work from the Development Team, ensuring that it meets the acceptance criteria and is aligned with the Product Backlog.
Managing Stakeholder Expectations: The Product Owner manages stakeholder expectations, communicating progress and changes to the product as needed. The Product Owner also ensures that stakeholders are aware of the priorities and goals of the product, and that their feedback is taken into account when prioritizing the Product Backlog.